## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project:
Week Of:
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
| 1 | Sean |  | processing strings from server (client side), still working on client connected list (client side), sending strings back from client to server | finish client connected list (client side)
| 2 | Thomas |  | server socket code and handles multiple clients (server side), classes player and state of game, communication protocol | finish server processing of strings (serer side), server communication for knowledge
| 3 | Allen |  | sketch of gui for client, html codes, switched to javafx (migration from node.js to javafx) | basic gui elements on client side (frontend)
| 4 | Jordan |  | developed client gui on node.js, but then migrated to javafx | event handlers for gui elements that allen develops
Final project documentation | 5 | All