## April 1
Group 4 |  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Project 5 |  |  |  |  | Sean Ennis | sennis3@uic.edu
Week Of: April 15th |  |  |  |  | Thomas Kubik | tkubik3@uic.edu
[5 empty] | Allen Chung | achung26@uic.edu
[5 empty] | Jordan Lee | jlee799@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week (Discussion) | Next Week (Action Items) | Issues
| A1 | All (Tentative) |  | Client GUI should have two phases - choosing items and actual game play (attacking, defending, etc.) | Finalize design GUI: Client side
| A2 | All (Tentative) |  | Server GUI should show all connected clients and who they are (Player ID) | Finalize design GUI: Server side
| A3 | All (Tentative) |  | Client and Server communicates through possibly strings | Finalize decision on communication method (String encoding)
| A4 | Sean Ennis (Tentative) |  | Client needs a way to choose who to attack and then send that choice to the server | Client Connected List (updating server)
| A5 | Sean Ennis (Tentative) |  | Client needs to see updated list after every round (Who died, etc.) | Client Connected List (updating client)
| A6 | Thomas Kubik (Tentative) |  | Client needs to recieve information from the server on the result of their action | Client side: processing server strings
| A7 | Thomas Kubik (Tentative) |  | The server will take in game state information (Who attacks who, defending, etc.) from the client | Server side: Processing strings from clients
| A8 | Allen Chung, Jordan Lee (Tentative) |  | Start on actually implementing the gui for the client | Client: Begin implementing gui and event listeners for different fields
| A9 | Allen Chung, Jordan Lee (Tentative) |  | Start on actually implementing the gui for the server | Server: Begin implementing gui
| A10 | Allen Chung, Jordan Lee (Tentative) |  | Start building "item choosing phase" (Code in items, stats?, choosing who goes first, etc. | Client: Begin implementing choosing items